## Test Execution Report
INTERFACE TEST EXECUTION REPORT
Project Name | Fast Food Delivery Application
Test Cycle | Interface Testing - Cycle 1
Test Date | 2025-12-10 to 2025-12-16
Tester | Test Engineer
EXECUTION SUMMARY | [7 empty] | Status | Count
Total Test Cases | 35 | [6 empty] | Passed | 28
Passed | 28 (80%) | [6 empty] | Failed | 4
Failed | 4 (11%) | [6 empty] | Blocked | 2
Blocked | 2 (6%) | [6 empty] | Not Run | 1
Not Run | 1 (3%)
Pass Rate | 80.00%
TEST CASE EXECUTION DETAILS | [7 empty] | Module | Pass | Failed | Blocked/Not Run
ID | Test Case Description | Module | Execution Result | Defect Reference | Executed By | Execution Date | Remarks | Module1 | 7 | 1 | 0
TC-USER-001 | Register with valid credentials | Module1 | Pass |  | Tester | 2025-12-10 |  | Module2 | 7 | 1 | 0
TC-USER-002 | Register with duplicate email | Module1 | Pass |  | Tester | 2025-12-10 |  | Module3 | 7 | 0 | 0
TC-USER-003 | Register with invalid email | Module1 | Failed | DEF-001 | Tester | 2025-12-10 | Email validation accepts 'test' without @domain - validator.isEmail() not implemented | Module4 | 6 | 2 | 2
TC-USER-004 | Register with weak password | Module1 | Failed | DEF-002 | Tester | 2025-12-10 | Password validation BVA bug: rejects 8-char passwords (uses > instead of >=) | Module5 | 1 | 0 | 1
TC-USER-005 | Register - DB connection error | Module1 | Pass |  | Tester | 2025-12-11
TC-USER-006 | Login with valid credentials | Module1 | Pass |  | Tester | 2025-12-11
TC-USER-007 | Login with non-existent user | Module1 | Pass |  | Tester | 2025-12-11
TC-USER-008 | Login with wrong password | Module1 | Pass |  | Tester | 2025-12-11
TC-FOOD-001 | Add food with valid data | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-002 | Add food without image | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-003 | Add food with invalid file type | Module2 | Failed | DEF-003 | Tester | 2025-12-12 | Security vulnerability: System accepts .exe files - MIME type validation missing in Multer
TC-FOOD-004 | Add food - Transaction rollback | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-005 | List all foods | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-006 | List foods - DB error | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-007 | Remove food - Atomic deletion | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-008 | Serve image file | Module2 | Pass |  | Tester | 2025-12-12
TC-CART-001 | Add new item to cart | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-002 | Add existing item | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-003 | Add without authentication | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-004 | Remove item - Decrement | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-005 | Remove item - Zero boundary | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-006 | Cart operations atomicity | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-007 | Get cart data | Module3 | Pass |  | Tester | 2025-12-13
TC-ORDER-001 | Place order successfully | Module4 | Pass |  | Tester | 2025-12-14
TC-ORDER-002 | Place order - Cart clearing | Module4 | Pass |  | Tester | 2025-12-14
TC-ORDER-003 | Stripe session creation | Module4 | Blocked |  | Tester | 2025-12-14 | Stripe API key not configured in test environment
TC-ORDER-004 | Stripe connection timeout | Module4 | Failed | DEF-004 | Tester | 2025-12-15 | No timeout handling: Application hangs for 30s when Stripe API unavailable
TC-ORDER-005 | Stripe retry logic | Module4 | Blocked |  | Tester | 2025-12-15 | Depends on TC-ORDER-003 - cannot test without Stripe config
TC-ORDER-006 | Payment verification - Success | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-007 | Payment verification - Cancel | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-008 | Payment - Transaction rollback | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-009 | Get user orders | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-010 | Update order status | Module4 | Pass |  | Tester | 2025-12-15
TC-STATIC-001 | Serve existing image | Module5 | Pass |  | Tester | 2025-12-16
TC-STATIC-002 | 404 for non-existent image | Module5 | Not Run |  |  |  | Low priority - time constraint