## Cover
Test Execution Report
Project | [Project ID / Name]
Program / Division | [Program / Division]
Build Version | [x.x]
Author / Technical Owner | [Tester Name]
Approval Status | Not Required
Reporting Date | [01-Apr-2009]
Location | PCB/Quality
Usage Note: The Testing Team will generate at least one Test Execution for each Build This template will not be used if there is a test execution management software replaces
Template Used:
Test Execution Report 1.0
For more information
IBM contact |  | Customer contact
Name |  | Name
Title |  | Title
IBM address line 1 |  | Customer address line 1
IBM address line 2 |  | Customer address line 2
Telephone |  | Telephone
Fax |  | Fax
E-mail |  | E-mail

## Interface Execution
INTERFACE TEST EXECUTION REPORT
Project Name | Fast Food Delivery Application
Test Cycle | Interface Testing - Cycle 1
Test Date | 2025-12-10 to 2025-12-16
Tester | Test Engineer
EXECUTION SUMMARY | [7 empty] | Status | Count
Total Test Cases | 35 | [6 empty] | Passed | 28
Passed | 28 (80%) | [6 empty] | Failed | 4
Failed | 4 (11%) | [6 empty] | Blocked | 2
Blocked | 2 (6%) | [6 empty] | Not Run | 1
Not Run | 1 (3%)
Pass Rate | 80.00%
TEST CASE EXECUTION DETAILS
ID | Test Case Description | Module | Execution Result | Defect Reference | Executed By | Execution Date | Remarks
TC-USER-001 | Register with valid credentials | Module1 | Pass |  | Tester | 2025-12-10
TC-USER-002 | Register with duplicate email | Module1 | Pass |  | Tester | 2025-12-10
TC-USER-003 | Register with invalid email | Module1 | Pass |  | Tester | 2025-12-10
TC-USER-004 | Register with weak password | Module1 | Pass |  | Tester | 2025-12-10
TC-USER-005 | Register - DB connection error | Module1 | Failed | DEF-001 | Tester | 2025-12-11 | MongoDB timeout not handled gracefully
TC-USER-006 | Login with valid credentials | Module1 | Pass |  | Tester | 2025-12-11
TC-USER-007 | Login with non-existent user | Module1 | Pass |  | Tester | 2025-12-11
TC-USER-008 | Login with wrong password | Module1 | Pass |  | Tester | 2025-12-11
TC-FOOD-001 | Add food with valid data | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-002 | Add food without image | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-003 | Add food with invalid file type | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-004 | Add food - Transaction rollback | Module2 | Failed | DEF-002 | Tester | 2025-12-12 | Image not deleted when DB save fails
TC-FOOD-005 | List all foods | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-006 | List foods - DB error | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-007 | Remove food - Atomic deletion | Module2 | Pass |  | Tester | 2025-12-12
TC-FOOD-008 | Serve image file | Module2 | Pass |  | Tester | 2025-12-12
TC-CART-001 | Add new item to cart | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-002 | Add existing item | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-003 | Add without authentication | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-004 | Remove item - Decrement | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-005 | Remove item - Zero boundary | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-006 | Cart operations atomicity | Module3 | Pass |  | Tester | 2025-12-13
TC-CART-007 | Get cart data | Module3 | Pass |  | Tester | 2025-12-13
TC-ORDER-001 | Place order successfully | Module4 | Pass |  | Tester | 2025-12-14
TC-ORDER-002 | Place order - Cart clearing | Module4 | Pass |  | Tester | 2025-12-14
TC-ORDER-003 | Stripe session creation | Module4 | Blocked |  | Tester | 2025-12-14 | Stripe API key not configured in test env
TC-ORDER-004 | Stripe connection timeout | Module4 | Failed | DEF-003 | Tester | 2025-12-15 | No retry mechanism implemented
TC-ORDER-005 | Stripe retry logic | Module4 | Blocked |  | Tester | 2025-12-15 | Depends on TC-ORDER-003
TC-ORDER-006 | Payment verification - Success | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-007 | Payment verification - Cancel | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-008 | Payment - Transaction rollback | Module4 | Failed | DEF-004 | Tester | 2025-12-15 | Orphan order record found
TC-ORDER-009 | Get user orders | Module4 | Pass |  | Tester | 2025-12-15
TC-ORDER-010 | Update order status | Module4 | Pass |  | Tester | 2025-12-15
TC-STATIC-001 | Serve existing image | Module5 | Pass |  | Tester | 2025-12-16
TC-STATIC-002 | 404 for non-existent image | Module5 | Not Run |  |  |  | Low priority - time constraint

## Functional
INTERFACE TEST EXECUTION REPORT
Project Name | Fast Food Delivery Application
Test Cycle | Functional Testing - Cycle 1
Test Date | 2025-12-10 to 2025-12-16
Tester | Test Engineer
EXECUTION SUMMARY
Total Test Cases | 29
Passed | 29(100%)
Failed | 0
Blocked | 0
Not Run | 0
Pass Rate | 100%
TEST CASE EXECUTION DETAILS | [7 empty] | Passed | 29
ID | Test Case Description | Module | Execution Result | Defect Reference | Executed By | Execution Date | Remarks | Failed | 0
FORM FUNCTIONALITY | [7 empty] | Not Run | 0
TC_FORM_01 | Add new data using form | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Form UI verification | Blocked | 0
TC_FORM_02 | Submit form with valid data | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Valid form submission | Total executed TC / Total TC | 29/29
TC_FORM_03 | Submit form with empty required fields | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Required field validation
TC_FORM_04 | Submit form with invalid data format | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Data format validation
TC_FORM_05 | Verify error message when invalid input is entered | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Error message display
TC_FORM_06 | Verify data is saved after form submission | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Data persistence
TC_FORM_07 | Add new data using form | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Create operation
TC_FORM_08 | Update existing data using form | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Update operation
TC_FORM_09 | View data details in form | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Read operation
TC_FORM_10 | Delete data using form | Module1 | Pass | N/A | Dieu Linh | 16/12/2025 | Delete operation
LINK TESTING
TC_LINK_01 | Verify all internal links navigate to correct pages | Module2 | Pass | N/A | Customer1 | 16/12/2025 | Internal link navigation
TC_LINK_02 | Verify internal links work from different pages | Module2 | Pass | N/A | Customer1 | 16/12/2025 | Internal link consistency
TC_LINK_03 | Verify external links (Stripe API) are accessible | Module2 | Pass | N/A | Customer1 | 16/12/2025 | External link integration
TC_LINK_04 | Verify external links open correct external resources | Module2 | Pass | N/A | Customer1 | 16/12/2025 | External link validation
TC_LINK_05 | Verify system does not contain broken internal links | Module2 | Pass | N/A | Customer1 | 16/12/2025 | Broken link check
TC_LINK_06 | Verify system handles unreachable external links gracefully | Module2 | Pass | N/A | Customer1 | 16/12/2025 | External link failure handling
TC_LINK_07 | Verify access to non-existing pages is prevented | Module2 | Pass | N/A | Customer1 | 16/12/2025 | Invalid page access
TC_LINK_08 | Verify system redirects user when accessing invalid pages | Module2 | Pass | N/A | Customer1 | 16/12/2025 | Page access control
TC_LINK_09 | Verify system redirects user when accessing invalid pages | Module2 | Pass | N/A | Customer1 | 16/12/2025 | Page access control
BUSINESS WORKFLOW
TC_BW_01 | Verify end-to-end order workflow | Module3 | Pass | N/A | Customer1 | 16/12/2025 | End-to-End workflow
TC_BW_02 | Verify workflow from login to successful payment | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Full business flow
TC_BW_03 | Verify data consistency across pages | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Data consistency
TC_BW_04 | Verify data consistency after page refresh | Module3 | Pass | N/A | Customer1 | 16/12/2025 | State persistence
TC_BW_05 | Verify system behavior when payment is cancelled | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Interrupted workflow
TC_BW_06 | Verify workflow when user navigates back during checkout | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Navigation handling
TC_BW_07 | Verify system prevents duplicate orders on repeated payment | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Duplicate prevention
TC_BW_08 | Verify redirection after successful login | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Redirect validation
TC_BW_09 | Verify redirection after successful payment | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Post-payment redirect
TC_BW_10 | Verify redirection when accessing protected pages | Module3 | Pass | N/A | Customer1 | 16/12/2025 | Access control
TC-STATIC-002 | 404 for non-existent image | Module5 | Not Run

## Compatibility
Last update: | 2009-05-25
Test Cases | Execution Result | Defect Refefence | Remarks | Passed | 12
TC_BC_01 | Passed |  |  | Failed | 0
TC_BC_02 | Passed |  |  | Not Run | 0
TC_BC_04 | Passed |  |  | Blocked | 0
TC_BC_05 | Passed |  |  | Total executed TC / Total TC | 12 / 12
TC_BC_06 | Passed
TC_BC_07 | Passed
TC_OSC_01 | Passed
TC_OSC_02 | Passed
TC_OSC_03 | Passed
TC_OSC_04 | Passed
TC_OSC_05 | Passed
TC_OSC_06 | Passed
Insert above
Note on C4: Required status: Passed / Failed

## Database
Last update: | 2009-05-25
Test Cases | Execution Result | Defect Refefence | Remarks | Passed | 12
TC_DI_01 | Passed | N/A |  | Failed | 1
TC_DI_02 | Passed | N/A |  | N/A | 2
TC_DI_03 | Passed | N/A |  | Blocked | 0
TC_DI_04 | Passed | N/A |  | Total executed TC / Total TC | 13 / 15
TC_DI_05 | Passed | N/A
TC_DI_01 | Passed | N/A
TC_DI_02 | Passed | N/A
TC_DI_03 | Passed | N/A
TC_DI_04 | Passed | N/A
TC_DI_05 | Failed | N/A
TC_DC_01 | Passed | N/A
TC_DC_02 | Passed | N/A
TC_DC_03 | Passed | N/A
TC_DC_04 | N/A | N/A
TC_DC_05 | N/A | N/A
Insert above
Note on C4: Required status: Passed / Failed

## Usability
Last update: | 2009-05-25
Test Cases | Execution Result | Defect Refefence | Remarks | Passed | 13
TC-01 | Passed | N/A |  | Failed | 0
TC-02 | Passed | N/A |  | Not Run | 0
TC-03 | Passed | N/A |  | Blocked | 0
TC-04 | Passed | N/A |  | Total executed TC / Total TC | 13 / 13
TC-05 | Passed | N/A
TC-06 | Passed | N/A
TC-07 | Passed | N/A
TC-08 | Passed | N/A
TC-09 | Passed | N/A
TC-10 | Passed | N/A
TC-11 | Passed | N/A
TC-12 | Passed | N/A
TC-13 | Passed | N/A
Insert above
Note on C4: Required status: Passed / Failed

## Performance
Last update: | 2009-05-25
Test Cases | Execution Result | Defect Refefence | Remarks | Passed | 6
PT_LD_01 | Passed |  |  | Failed | 0
PT_LD_02 | Passed |  |  | Not Run | 0
PT_CN_01 | Passed |  |  | Blocked | 0
PT_ST_01 | Passed |  |  | Total executed TC / Total TC | 6 / 6
PT_ST_02 | Passed
PT_RC_01 | Passed
Insert above
Note on C4: Required status: Passed / Failed

## Doc Control
This information is for template control purpose only. This page can be removed when an actual document is made.
Document Control Page
Test Execution Report Template
Template version: | 1.0
Template status: | Approved
Template file name: | Test Execution Report.xls
Revision history of this template
Version No. | Revision Date | Change Description | Author's Name | Approver's Name | Approver's Title
0.6 | 2009-07-28 | Draft | SEPG
0.9 | 2009-07-29 | Reviewed | SEPG
0.95 | 2009-08-25 | Update based on review of Aug 19 with PI task force | SEPG
1.0 | 2009-09-11 | Approved |  | Hy TQ | DE Manager
Usage notes:
Use this template to develop the various kinds of documents. The content of the document are subjected to be filled and changed in the document, according to the following legends:
Blue comment: The brief guidance on how to fill the sections. These parts shall be removed from the actual documents.
Example (Red text): The brief example to illustrate the sections. These parts shall be removed from the actual documents.
[Text in brackets]: Shall be replaced with the actual contents.

## Tailoring (hidden)
Tailoring
Use this Tab to change standard criteria defaults and overall score defaults
Standard Criteria | Small | Large
#REF!
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | Yes | Yes
#REF!
#REF! | No | Yes
#REF! | No | Yes
#REF! | Yes | Yes
#REF!
#REF! | Yes | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF!
#REF! | Yes | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF!
#REF! | Yes | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF!
#REF! | Yes | Yes
#REF! | No | Yes
#REF! | No | Yes
#REF! | Yes | Yes
#REF! | No | Yes
Overall Score Reduction
Severity | Threshold (Number of items that trigger an overall score reduction) | If number of items by severity in review log is equal of greater than threshold, overall score will be reduced by | Associated Risk Assessment+Print_Area
#REF! | 1 | -30 | Red
#REF! | 3 | -15 | Yellow
#REF!
#REF! | 4 | -3.75 | Green
#REF! | 4 | -2.25 | Green